## Slide 1: Lessons Learned: Viewpoints on Increasing Analytical Capabilities in an Organization Predictive Modeling Projects from a Company Perspective
Greg Hansen, FCAS, MAAA
Actuarial Research Leader
Westfield Insurance
Westfield Center, Ohio
Lessons Learned
(the Hard Way)
from Predictive Modeling Projects

## Slide 2: Antitrust Notice
The Casualty Actuarial Society is committed to adhering strictly to the letter and spirit of the antitrust laws. Seminars conducted under the auspices of the CAS are designed solely to provide a forum for the expression of various points of view on topics described in the programs or agendas for such meetings.
Under no circumstances shall CAS seminars be used as a means for competing companies or firms to reach any understanding – expressed or implied – that restricts competition or in any way impairs the ability of members to exercise independent business judgment regarding matters affecting competition.
It is the responsibility of all seminar participants to be aware of antitrust regulations, to prevent any written or verbal discussions that appear to violate these laws, and to adhere in every respect to the CAS antitrust compliance policy.

## Slide 3: Westfield Insurance
Founded in 1848
~$1.5 Billion Direct Written Premium
  $0.9 Billion Commercial / Surety
  $0.6 Billion Personal
Produces business exclusively through independent agencies

## Slide 4: A Basic Modeling Process
Business
Purpose
Monitor and
Maintain
Implement
Model
Data

## Slide 5: Lesson One
Modeling projects don’t begin with modeling. They begin with:
  A business question / strategic goal
  Research / data collection
Modeling projects don’t end with a model. They end with:
  IT implementation
  Business implementation
  Monitoring and Maintenance
    (a.k.a. “living with the models”)

## Slide 6: Business Implementation
Chart: Monitoring Report: Underwriting Model Utilization
| Year1 Q1 | Year1 Q2 | Year1 Q3 | Year1 Q4 | Year2 Q1 | Year2 Q2 | Year2 Q3 | Year2 Q4 | Year3 Q1 | Year3 Q2 | Year3 Q3 | Year3 Q4
Series 1 | 0.75825 | 0.73661 | 0.70091 | 0.69388 | 0.75035 | 0.7612 | 0.75126 | 0.78616 | 0.81495 | 0.80659 | 0.8317 | 0.85421
Models rolled out
Implemented Performance Standard
Raised Perf.
Standard

## Slide 7: A Basic Modeling Process
Data
Model
Implement
Scaled to Actuarial Effort

## Slide 8: Lesson Two
Modeling can be a small part of even the actuarial / modeling project
Expect to do a lot more than just modeling

## Slide 9: A Basic Modeling Process
Data
Model
Implement
Scaled to Total Project Effort

## Slide 10: Lesson Three
Modeling is a tiny portion of the total modeling project
  Recent (large) project:
    Estimated Actuarial Hours: 6,000
    Estimated IT / Business Hours: 25,000
Make decisions based on the total scope of the project

## Slide 11: A Tale of Two Projects
Two actual projects that I’ve managed over the last several years
  Comparable scope
  Comparable cost
  Comparable expected business value
  Both were ultimately successful
  Biggest difference: time to complete

## Slide 12
Data
Model
Implement
12 months
6 m
20 months
6 m
2
12 months
Total Duration: 40+ months
Total: 12 months
Project A
Project B

## Slide 13: Lesson Four
Project A: Project manager not engaged until after the model was built
Project B: Project manager engaged before the project started
Effective and timely project management is critical

## Slide 14: Lesson Five
Project A: IT work did not start until months after the model was built
Project B: IT work ran concurrently with the model building process
Begin communication between IT, modeling, and business units early

## Slide 15: Lesson Six
Project A: Model was built entirely in-house
Project B: Used experienced consultants with whom we had an established relationship
The right partners can help you get done faster (and better)

## Slide 16: Lesson Seven
Project A: Model built “on the side” by part time resources
Project B: Had full time staff from day one (on both the company and the consulting side)
Unless time is no issue, don’t try to build models “on the side”

## Slide 17: Lesson Eight
Project A: The first project of its kind for our company
Project B: The fourth project of its kind
It gets easier over time
Look for repeatable processes

## Slide 18: Lesson Nine
Project A: Was not a corporate priority until the modeling portion was complete
Project B: Was a corporate priority before the project started
Models should to be driven by a business purpose (see Lesson One)

## Slide 19: Closing Thoughts
Don’t forget about culture change
  Effective communication and reporting
View wild claims of benefits with skepticism
Building a model has different challenges than owning one
Each project brings new challenges, new lessons